## Sheet1
Possible Improvements as Listed by Jessica - Oct 10, 2024
As discussed December 12, 2024 |  | logged by Bryan McGinnis
Item | Comments 12/12/2024 | Task | Assigned
Crosswalk Repainting x3 (and new?) | New ones suggested for Owl/Wildwood and Grotto/Wildwood | Coordingate with Roads Safety TF
Vegetation Removal on blind corner(s) | Several places need initial cleaing and/or ongoing attention. | Determine equipment needed and costs for equipmnent and ongoing | Cora
Traffic Mirrors x3 - -prices vary greatly on vendor | No one has identified any nearby location of installed mirror(s). | Find specific costs | Karen
Electronic Speed Signs | Needed for Wildwood and eastern Hall | Contact County and Mahtomedi on experience, reliability, & specific pricing | Mary
Sharrows | On Hall and & Wildwood | Where to place? | Ben
Bike Route Road Stencil | Would need to be done with each road re-paving | Where to place? | Ben
Sign Enhancement | Put larger background plate behind existing small LL signs, to make more visible | Need to clarify how this will be done.
Sign with "Rules" | For education on "rules of the road" etc | See what LL and other communities are doing or plan on for rules, sharing the road, etc. | Jane
Lighting of Trail | Need not defined. Could be extra street light(s). | Where to place? | None
Bike Repair Station | Not thought to be needed in Birchwood Village | None | None